## Schedule
# | Task_Name | Duration(Days) | Start_Date | Finish_Date
1 | Project Planning | 4 | 2018-02-16 | 2018-02-21 | Project planing, Requirement analysis,Development, testing and completion.
1.1 | Initiation | 2 | 2018-02-16 | 2018-02-18
1.2 | Project Planning | 2 | 2018-02-19 | 2018-02-21 |  | Critical Paths
2 | Requirement | 20 | 2018-04-02 | 2018-04-27 |  | Design Phase has the dependency with Requirements signoff | 27/04/2018 To 01/05/2018
2.1 | Requirement Analysis | 5 | 2018-04-02 | 2018-04-06 |  |  | 16/05/2018 To 17/05/2018
2.2 | Technical Discussion | 5 | 2018-04-09 | 2018-04-13 |  | Milestone1 has dependency with DataBase Design | 01/06/2018 To 04/06/2018
2.3 | Requirement Review & Rework | 5 | 2018-04-16 | 2018-04-20 |  | Dvelopment has dependency with MileStone1 | 24/06/2018 To 25/06/2018
2.4 | Requirement Signoff | 5 | 2018-04-23 | 2018-04-27 |  | Testing has Dependency with Development | 17/08/2018 To 02/07/2018
3 | Design | 24 | 2018-05-01 | 2018-06-01 |  | Bugfixing has Dependency with Testing | 28/09/2018 To 18/08/2018
3.1 | Design Templates | 12 | 2018-05-01 | 2018-05-16 |  | Milestone2 has dependency with Milestone1(bugfixing) | 09/10/2018 To 10/10/2018
3.2 | Design Templates Review and rework | 4 | 2018-05-17 | 2018-06-22 |  | UAT bugfixing has dependency with MileStone2 | 28/12/2018 To 17/01/2019
3.3 | Database Design | 8 | 2018-05-23 | 2018-06-01 |  | UAT Signoff has dependency with UAT bug fix | 23/01/2019 To 24/01/2019
4 | APP's Development & Testing | 150 | 2018-06-04 | 2018-12-28 |  | Deployment on client server has dependency with UAT signoff | 28/01/2019 To 29/01/2019
4.1 | Milestone 1(Login, Registration, landing screen) | 20 | 2018-06-04 | 2018-06-24 |  | Go Live has dependency with Deployment on client server | 29/01/2019 To 30/01/2019
4.1.1 | Development | 40 | 2018-06-25 | 2018-08-17 |  | Peoject Closure has dependency with Go Live | 30/01/2019 To 31/01/2019
4.1.2 | Testing | 65 | 2018-07-02 | 2018-09-28
4.1.3 | Bugfixing | 15 | 2018-08-18 | 2018-10-09
4.2 | Milestone 2(Remaining APP functionalities) | 20 | 2018-10-10 | 2018-10-30
4.2.1 | Development | 40 | 2018-11-01 | 2018-12-10
4.2.1 | Testing | 65 | 2018-09-28 | 2018-12-28
4.2.3 | Bugfixing | 15 | 2018-12-10 | 2018-12-28
5 | UAT & Signoff |  | 2018-12-31 | 27-04-16 5:00 PM | UAT and Signoff , deployment and Closure.
5.1 | UAT | 10 | 2018-12-31 | 2019-01-16
5.2 | UAT bug fix | 5 | 2019-01-17 | 2019-01-23
5.3 | UAT Signoff | 2 | 2019-01-24 | 2019-01-28
6 | Deployment on client server | 1 | 2019-01-29 | 2019-01-29
7 | Go Live | 1 | 2019-01-30 | 2019-01-30
8 | Project Closure | 1 | 2019-01-31 | 2019-01-31